## July-19
Property Project Tasks
Task no. | Task name | Initial date | Completion date | User | Status | Phase | Ref task
20190703.01 | Project Structure | 2019-07-03 | 2019-03-07 | Shafiq | Done | Primary | N/A
20190707.01 | Implementation of base structure | 2019-07-07 | 2019-07-11 | Shafiq | Done | Primary | N/A
20190716.01 | Merged base structure on git | 2019-07-16 | 2019-07-16 | Shafiq | Done | Primary | N/A
20190717.01 | Implementation of template | 2019-07-17 | N/A | Shafiq | on-going | Primary | N/A